## QC Matrix
Test ID | Priority | Area | Scenario | Preconditions | Steps | Expected Result | Failure Signal | Owner | Status | Last Run | Notes
QC-001 | Critical | Enrollment | Bind new device with EMI terms | Dealer logged in; unused key available; user app freshly installed | Create enrollment; enter customer data; enter total price/down payment/interest/duration/grace; confirm with user app code | Device becomes enrolled; key count decreases; EMI schedule created only after confirm | Key count unchanged or schedule missing | Flutter+Backend | Not Run | Physical test required
QC-002 | Critical | Enrollment | Wrong 6-digit code is rejected | Pending enrollment exists | Enter wrong code in user app | User app shows readable failure and backend does not activate device | Device activates with wrong code | Kotlin+Backend | Not Run
QC-003 | Critical | EMI Schedule | 3-month EMI produces exactly 3 local rows | Device confirmed with 3-month EMI | Open user app dashboard; inspect local schedule/debug logs | Only 3 due rows exist; no month 4 reminder | Month 4 reminder appears | Kotlin | Not Run
QC-004 | Critical | Location | Fresh pull location succeeds | Dealer and user app online; location permission granted | Tap Pull Location once; watch logs | FCM received; GPS read; report accepted; dealer map updates | Accepted request but no map update | All | Not Run
QC-005 | Critical | Location | Repeated pull does not clog DB | Same as QC-004 | Tap Pull Location 5 times quickly | Only one active pull remains; UI cooldown shows | Multiple pending pulls pile up | Backend+Flutter | Not Run
QC-006 | Critical | Location | Stale location warning appears | Device offline or FCM unavailable | Tap Pull Location; wait timeout | Spinner stops; dealer sees pending/stale warning with timestamp | Spinner forever or previous location shown as live | Flutter | Not Run
QC-007 | Critical | Lock | Lock command confirms visibly | Device online; overlay/admin permission active | Submit lock request with reason/note | Dealer UI exits spinner and shows locked status | Device locks but dialog spins forever | All | Not Run
QC-008 | Critical | Unlock | Unlock command confirms visibly | Device locked and online | Submit unlock request | Dealer UI exits spinner and shows unlocked status | Device unlocks but UI remains pending | All | Not Run
QC-009 | Critical | Offline Unlock | OTP unlock works when offline | Device locked; offline secret provisioned | Disconnect internet; enter offline unlock OTP/code | Device unlocks locally and syncs when online | Device says no offline secret or status never syncs | Kotlin+Backend | Not Run
QC-010 | Critical | Offline Unlock | SMS OTP auto-read works | READ_SMS permission granted; SMS format known | Send valid offline unlock SMS to device | User app detects SMS and starts unlock flow | Message ignored | Kotlin | Not Run
QC-011 | Critical | Permission Tamper | Overlay permission turned off | Device enrolled and overlay permission initially granted | Open Android settings; disable display over other apps; return to user app or trigger dealer command | Backend receives degraded snapshot; dealer sees protection degraded quickly | Dealer still shows healthy | Kotlin+Backend+Flutter | Not Run
QC-012 | Critical | Permission Tamper | SMS permission turned off | Device enrolled and SMS permission initially granted | Disable SMS permission; return to user app or send OTP SMS | Backend receives SMS degraded snapshot; dealer sees SMS unlock degraded | No warning; OTP silently fails | Kotlin+Backend+Flutter | Not Run
QC-013 | Critical | Permission Tamper | Notification permission turned off | Device enrolled; notification permission initially granted | Disable notification permission; return to user app or send dealer message | Backend receives notification degraded snapshot; dealer sees degraded notification status | Dealer thinks notification delivered | Kotlin+Backend+Flutter | Not Run
QC-014 | Critical | App Removal | User app uninstalled or FCM token invalid | Device enrolled; backend has FCM token | Uninstall app if allowed or simulate invalid token; send command | Backend marks suspected app removal after FCM invalid response | Dealer only sees old status | Backend+Flutter | Not Run
QC-015 | High | Heartbeat | Device offline vs app removed distinction | Device enrolled | Turn off internet; do not uninstall app; wait heartbeat window | Dealer shows offline/delayed | not app removed | False uninstall alert | Backend+Flutter | Not Run
QC-016 | High | Dealer Message | Message sends quickly | Device online | Send message from dealer app | UI returns quickly; user app displays message/notification | Long spinner or delayed notification | All | Not Run
QC-017 | High | Evidence Vault | Real account requires evidence photos | Dealer real account logged in | Start binding; try to skip NID/face photos | Wizard blocks until required evidence captured | Enrollment completes without evidence | Flutter | Not Run
QC-018 | High | Evidence Vault | Demo account can skip vault requirement | Demo dealer logged in | Start demo enrollment | Demo flow does not block on Google Drive evidence | Demo blocked by evidence requirement | Flutter | Not Run
QC-019 | High | QR Enrollment | Missing AMAPI config is visible | Render AMAPI env intentionally missing in staging | Tap generate enrollment QR | Dealer sees clear setup error | Blank QR with no error | Backend+Flutter | Not Run
QC-020 | High | Login | Login screen does not expose backend URL | Invalid network/backend state | Open login; force login error | Error is human-readable and hides backend URL | Raw URL shown to dealer | Flutter | Not Run
QC-021 | Medium | Device List | Customer name visible | Device has customer data | Open device list and detail | Customer name and useful summary visible | Blank/unknown customer | Flutter+Backend | Not Run
QC-022 | Medium | Map | Open in Google Maps works | Device has valid location | Open location dialog; tap external maps action | Google Maps opens at coordinates | Button missing or opens wrong place | Flutter | Not Run
QC-023 | Medium | Rate Limit | Registered device action unaffected by Redis outage | Staging Redis unavailable | Send lock/location/message as registered dealer | Action accepted or fails open where safe | Redis blocks registered flow | Backend | Not Run
QC-024 | Medium | Recovery | Device token refresh repairs missing local token | Old enrolled app with no token | Trigger FCM/location or app startup refresh | Token saved and report works | 401 remains | Kotlin+Backend | Not Run
QC-025 | Medium | SSE | Dealer reconnect receives updates | Dealer app running; network toggled | Disconnect/reconnect network; send event | SSE reconnects and visible state refreshes | Updates only after manual refresh | Flutter+Backend | Not Run

## Permission Tamper
Test ID | Permission / setting | How to tamper | Expected app detection | Expected dealer visibility | Status | Notes
PERM-001 | Display over other apps / overlay | Android Settings > Apps > EMI user app > Display over other apps > Off | User app reports overlay_disabled at next lifecycle/FCM/service touchpoint | Dealer sees protection degraded | Not Run | Critical for partial lock
PERM-002 | SMS permission | Android Settings > Apps > EMI user app > Permissions > SMS > Deny | User app reports sms_disabled | Dealer sees SMS unlock degraded | Not Run | Needed for SMS unlock automation
PERM-003 | Notification permission | Android Settings > Apps > EMI user app > Notifications > Off | User app reports notifications_disabled | Dealer sees notifications degraded | Not Run | Avoid false delivered message confidence
PERM-004 | Location permission | Android Settings > Apps > EMI user app > Permissions > Location > Deny | User app reports location_disabled | Pull location becomes degraded/stale with clear reason | Not Run | Critical for pull location
PERM-005 | Battery optimization | Restrict background battery or enable deep sleep | User app reports battery_restricted when able | Dealer sees degraded/background risk | Not Run | Avoid false uninstall alert
PERM-006 | Device admin/profile owner | Remove admin if Android allows | User app reports device_admin_inactive | Dealer sees protection degraded | Not Run | Depends on device policy mode

## Fault Log
Fault ID | Date | Area | Symptom | Root Cause | Fix / Prevention | Status | Evidence Link
F-006 | 2026-05-11 | Dealer UI | Lock spinner can run indefinitely | No action-level timeout or confirmation fallback | Add timeout, polling/SSE handling, pending state | Open | docs/FAULT_LEDGER.md
F-007 | 2026-05-11 | Dealer UI | Errors disappear | Silent catch blocks | Replace silent catches with logging and user-safe messages | Open | docs/FAULT_LEDGER.md
F-010 | 2026-05-11 | User app permissions | Permission tamper makes app ineffective | Android settings can disable required runtime permissions | User app reports permission health and backend emits device_health_changed | Mitigated | docs/FAULT_LEDGER.md

## Release Signoff
Gate | Check | Pass/Fail | Owner | Notes
Backend | Syntax/build/test check passed |  | Backend developer
Dealer app | Flutter build and analyze checked |  | Flutter developer
User app | Gradle debug build checked |  | Kotlin developer
Docs | System map/API index/fault ledger updated |  | Builder
QC | Critical QC cases run on physical device |  | Tester
Deploy | Render deployment and logs verified |  | Backend developer
Rollback | Rollback path known before release |  | Builder